## Sheet1
Dự án | Xây dựng Website bán quần áo và phụ kiện
Công nghệ | REACT, REDUX, EXPRESS, NODE, MONGODB
Thành viên | Mai Văn Thinh - 3119410413
|  |  |  | September | [25 empty] | October | [30 empty] | November
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
Task name | Owner | Start date | End date | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Design System
Requirements | Thinh | 2022-09-19 | 2022-09-21 | Week 1 11: 100
Draw UML diagram |  | 2022-09-21 | 2022-09-30 | bar: Week 1 5 to Week 1 11
Build core Back-end |  | 2022-09-22 | 2022-09-27 | bar: Week 1 5 to Week 1 11
Build core Front-end |  | 2022-09-22 | 2022-09-29 | bar: Week 2 12 to Week 3 25
Design DB |  | 2022-09-22 | 2022-09-25 | bar: Week 2 12 to Week 3 25
Import location into DB |  | 2022-09-25 | 2022-09-30 | bar: Week 1 5 to Week 1 11
WEB FOR ADMINISTRATION Implement / Coding for Authentication, Authorization, Admin Module
Build common layout(Header, Body, Footer, Sidebar/Navbar) | Thinh | 2022-10-01 | 2022-10-02 | bar: Week 4 1
UI for Log-in, change password, forgot password |  | 2022-10-03 | 2022-10-04 | bar: Week 4 2 to Week 5 3
UI for Dashboard |  | 2022-10-05 | 2022-10-06 | bar: Week 5 4 to Week 5 5
UI for Manage Users |  | 2022-10-07 | 2022-10-08 | bar: Week 5 6 to Week 5 7
UI for Manage products |  | 2022-10-09 | 2022-10-10 | bar: Week 5 8 to Week 5 9
UI for Manage category |  | 2022-10-11 | 2022-10-12 | bar: Week 6 10 to Week 6 11
UI for Manage orders |  | 2022-10-13 | 2022-10-14 | bar: Week 6 12 to Week 6 13
UI for Reviews |  | 2022-10-15 | 2022-10-16 | bar: Week 6 14 to Week 6 15
UI for User information |  | 2022-10-17 | 2022-10-18 | bar: Week 6 16 to Week 7 17
Integrate API to Front-end |  | 2022-10-19 | 2022-10-19 | bar: Week 7 18
API for Log-in, change password, forgot password |  | 2022-10-01 | 2022-10-02 | bar: Week 4 1 to Week 4 2
API for Dashboard |  | 2022-10-03 | 2022-10-04 | bar: Week 5 3 to Week 5 4
API for Manage Users |  | 2022-10-05 | 2022-10-06 | bar: Week 5 5 to Week 5 6
API for Manage products |  | 2022-10-07 | 2022-10-08 | bar: Week 5 7 to Week 5 8
API for Manage category |  | 2022-10-09 | 2022-10-10 | bar: Week 5 9 to Week 6 10
API for Manage orders |  | 2022-10-11 | 2022-10-12 | bar: Week 6 11 to Week 6 12
API for Reviews |  | 2022-10-13 | 2022-10-14 | bar: Week 6 13 to Week 6 14
API for User information |  | 2022-10-15 | 2022-10-16 | bar: Week 6 15 to Week 6 16
WEB FOR USERS
Implement / Coding for Authentication, Authorization
Build common layout(Header, Body, Footer, Sidebar/Navbar) | Thinh | 2022-10-13 | 2022-10-14 | bar: Week 6 13 to Week 6 14
UI for Sign-up, Sign-in, change password, forgot password |  | 2022-10-15 | 2022-10-16 | bar: Week 6 15 to Week 6 16
Integrate API to Front-end |  | 2022-10-19 | 2022-10-19 | bar: Week 7 19
API for Sign-up, Sign-in,change password, forgot password |  | 2022-10-17 | 2022-10-18 | bar: Week 7 17 to Week 7 18
Implement / Coding for Users Module
UI for Home page | Thinh | 2022-10-20 | 2022-10-21 | bar: Week 7 20 to Week 7 21
UI for Products page |  | 2022-10-22 | 2022-10-23 | bar: Week 7 22 to Week 7 23
UI for Contacts page |  | 2022-10-24 | 2022-10-25 | bar: Week 8 24 to Week 8 25
UI for About page |  | 2022-10-26 | 2022-10-27 | bar: Week 8 26 to Week 8 27
Integrate API to Front-end |  | 2022-10-30 | 2022-10-30 | bar: Week 8 30
API for Product |  | 2022-10-28 | 2022-10-29 | bar: Week 8 28 to Week 8 29
Implement / Coding for Candidate Module
UI for Cart | Thinh | 2022-10-31 | 2022-11-01 | bar: Week 9 31 to Week 9 1
UI for Order |  | 2022-11-02 | 2022-11-03 | bar: Week 9 2 to Week 9 3
UI for User profile |  | 2022-11-04 | 2022-11-05 | bar: Week 9 4 to Week 9 5
UI for Views Orders |  | 2022-11-06 | 2022-11-07 | bar: Week 9 6 to Week 10 7
Integrate API to Front-end |  | 2022-11-16 | 2022-11-16 | bar: Week 11 16
API for Cart |  | 2022-11-08 | 2022-11-09 | bar: Week 10 8 to Week 10 9
API for Order |  | 2022-11-10 | 2022-11-11 | bar: Week 10 10 to Week 10 11
API for User profile |  | 2022-11-12 | 2022-11-13 | bar: Week 10 12 to Week 10 13
API for Views Order |  | 2022-11-14 | 2022-11-15 | bar: Week 11 14 to Week 11 15
Formulas:
End date = [Start date]+1
End date = [Start date]
Start date = [End date, row above]+1
Start date = [Start date, row above]+2